## Sheet1
Activity | Start Date | End Date | % Complete | Status
Requirements gathering | 2023-09-01 | 2023-09-11 | 100% | Complete
Stories creation | 2023-09-12 | 2023-09-22 | 100% | Complete
stories sign-off | 2023-09-23 | 2023-10-03 | 0% | In_Progress
Schedule update | 2023-10-04 | 2023-10-14 | 0% | On_Hold
Execution | 2023-10-15 | 2023-10-25 | 0% | Not_Started
Deliver | 2023-10-26 | 2023-11-05 | 0% | Not_Started
Close | 2023-11-06 | 2023-11-16 | 0% | Not_Started
Formulas:
End Date = [Start Date]+10
Start Date = [End Date, row above]+1